Balfour Beatty Highways Hub

To Residents,

Granville House

St Georges Road

Donnington Wood

Telford

TF27RA

Highways Adoption Works in your area

Lightmoor Way, Lightmoor

Dear Resident,

Telford and Wrekin Council are continuing work on behalf of Bournville Village Trust as part of the highway’s adoption process at both entrances to Lightmoor Village. The works include footway & carriageway improvement works on Lightmoor Way, Lightmoor. Specifically: streetlighting, kerbing, block paving, ironworks, footway surfacing, and carriageway resurfacing. Works will be completed by Balfour Beatty and specialist sub-contractors MSM, Tarmac and Quantum Traffic Management

When are we planning to deliver this work?

The work is ongoing and will be completed by 27th March 2026 (weekdays only) weather permitting. Please see below the phased traffic management for these works:

Phase 1 – Lightmoor Way South (04/02/2026-05/03/2026)

Kerbing, signage, street lighting and gully works. To be completed with localised signing and guarding with roads remaining open at all times

Phase 2 - Wellington Road (02/03/2026-13/03/2026)

Bus Stop Relocation, Street lighting and footpath resurfacing. To be completed under 24hr multi-way traffic lights (between the junction with The Bache and Round House Park)

Phase 3 Lightmoor Way South (16/03/2026-20/03/2026)

Carriageway Resurfacing . To be completed under a 24hr road closure (from A4169 mini roundabout to Little Flint)

Phase 4 Wellington Road (23/03/2026-27/03/2026)

Carriageway Resurfacing . To be completed under a 24hr road closure (from Wellington Road to Old Canal Mews)

We will have our dedicated teams on site to assist you during this time to help you get past the working areas safely should you need to do. Whilst we will endeavour to minimise disruption, we ask that you keep vehicle movements to an absolute minimum and not to park on the road. Please also ensure that children are supervised, do not play near the working areas and all pets are kept away from the works.

Information about access to your property

Access will be maintained for residents and for emergency vehicles when it is safe to do so, alternatively all vehicular traffic will be required to follow the signed diversion route. Dedicated site staff will be onsite to assist you during this closure, although some disruption should be expected. Should you choose to drive through the road closure, please be aware that this will be at your own risk. We will try to cause as little inconvenience as possible and really appreciate your co-operation whilst we are undertaking the works.

If you have any special access requirements while the works are in progress or need to contact Balfour Beatty about these improvements please contact us at our new Telford Highways Hub: TelfordHighways@Balfourbeatty.com and a member of our team will be in contact with you shortly.

Thank you for your co-operation whilst we deliver these improvements in your area.